## Revision History
Revision History
Version | Date | Name | Changes
1 | xx-xx-20xx | Flo Samuels | Initial Release
1.1 | xx-xx-20xx | Flo Samuels | Reasons for revisions
1.2 | xx-xx-20xx | Flo Samuels | Reasons for revisions
1.3 | xx-xx-20xx | Flo Samuels | Reasons for revisions
C:\SOFTWARE DEV\Project Planning\Estimating Template.doc |  |  |  | Creation Date: 07/23/20xx
Version: 1.3 |  |  |  | Revision Date: 11/21/20xx

## Overview
DOCUMENT REVISION HISTORY
Version | Date | Name | Description
1 | xx-xx-20xx | Your Name | Initial Release.
1.1 | Date | Your Name | Short Description of Changes
Overview
Estimating software size, effort, cost, and critical computer resource needs is done when the software development plan is being developed. The estimates are used to determine project schedule dates, budget, and potential impacts on computer resources. These estimates are revisited at major project milestones to determine if they have changed and if the changes will affect the project schedule, budget, or computer needs.
At project end, estimates are compared to actuals. If there is a significant difference (over 15%), the project manager must analyze the data to determine the reason(s). Factors such as changes in scope or the addition or loss of resources, etc. should be examined for their effect on the estimates. The purpose of this analysis is to refine the project manager's estimating capabilities to ensure future projects are better estimated so that schedules will become more accurate.
Project elements that are estimated include:
Software size (code and documentation)
Project effort (hours to do each task)
Project cost (hours times cost per hour for each resource or average cost times total effort)
Critical computer resources (hardware, server space, server time, licensing requirements, etc.)
Software Size Estimating Method
Function Points (two worksheets)
Documentation
Project Effort Estimating Methods
Function Points (two worksheets)
Weighted Average (WAVE)
Use Cases
Project Cost Estimating Method
Cost
Critical Computer Resources Estimating Method
Computer Resources

## Function Points
Function Points Guidelines
Function point counts are prepared as follows:
TOP TABLE
* Five key parameters of the product are counted or estimated.
* Weightings, adjusted for complexity, are applied to the five parameter counts and the results summed to arrive at an unadjusted total
BOTTOM TABLE
* The unadjusted total in the top table (line 23) is modified with an adjustment multiplier (line 24) that is based on the rating of project factors, calculated in the bottom table, to yield the final adjusted function point count (line 25).
Function Point Worksheet
Enter the number of instances for each parameter under the appropriate column(s) reflecting complexity.
If more than one language is being used, complete a worksheet for each language.
Do not make entries in shaded rows or columns.
| Function Point Parameters | Low Complexity Weighting | Calc | Average Complexity Weighting | Calc | High Complexity Weighting | Calc | Totals
| External Inputs |  | 0 |  | 0 |  | 0 | 0
| External Outputs |  | 0 |  | 0 |  | 0 | 0
| Logical Master Files |  | 0 |  | 0 |  | 0 | 0
| Interface Files |  | 0 |  | 0 |  | 0 | 0
| Inquiries |  | 0 |  | 0 |  | 0 | 0
[7 empty] | Unadjusted Total | 0
[7 empty] | Adjustment Multiplier (See Table below) | 0
[7 empty] | Adjusted Function Points | 0
Adjustment Multiplier
To develop the adjustment multiplier, the project influence factors in the Table below are evaluated by the project manager/project team as follows:
* Each factor is rated on a scale of 0 to 5 using the rating considerations. Use 0 to eliminate factors which are not present.
* The sum of these ratings is converted to an adjustment multiplier in the last line of the Table.
Do not make entries in shaded rows or columns.
Rating
| Project Influence Factors | Rating Considerations | [7 empty] | (0 - 5)
| Data Communications | 0 to 5; where 0 = batch; 1 = remote printing or data entry; 2 = remote printing and data entry; 3 = teleprocessing front end; 4 = significant teleprocessing; 5 = dominantly teleprocessing
| Distributed Functions | 0 to 5; where 0 = single processor; 1 = prepares data for other processors; 2/3/4 - distributed over few to several processors; 5 = dynamically performed on many processors
| Performance Objectives | 0 to 5; where 0 = no special performance criteria required and 5 = very stringent performance criteria requiring considerable effort to meet
| Heavily Used Configuration | 0 to 5; where 0 = no special usage constraints and 5 = anticipated heavy usage (loading) requires considerable effort to satisfy
| Transaction Rate | 0 to 5; where 0 = transaction volumes are not significant and 5 = high transaction rates likely to stress the application requiring considerable effort to meet desired throughputs
| On-line Data Entry | 0 to 5; where 0 = fewer than 15% of transactions are interactive and 5 = 50% or more of transactions are interactive
| End User Efficiency | 0 to 5; where 0 = no end users or no special end user requirements and 5 = stated requirements for end user efficiency are stringent requiring considerable effort to meet
| On-line Update | 0 to 5; where 0 = none required and 5 = mandatory and especially difficult (data integrity)
| Complex Processing | 0 to 5; where 0 = none required and 5 = extensive logical decisions, complicated mathematics, tricky exception handling, or elaborate security schemes
| Reusability | 0 to 5; where 0 = functionality to stay local to the current application required and 5 = much of the functionality is intended for widespread use in other applications
| Installation Ease | 0 to 5; where 0 = no special considerations and 5 = installation ease is both important and so stringent that it requires special effort to accomplish a satisfactory installation
| Operational Ease of Use | 0 to 5; where 0 = no special considerations and 5 = operational ease of use so important that it requires special effort to accomplish
| Multiple Sites | 0 to 5; where 0 = only one planned using site and 5 = intended for many diverse locations
| Facilitate Change | 0 to 5; where 0 = no user supported change and 5 = application is designed specifically to accommodate frequent user changes to control data or tables they maintain with the aid of this application
[9 empty] | Sum of Project Influence Factors | 0
[9 empty] | Adjustment Multiplier = (Sum * .01) + .65 | 0

## FP to Size and Effort
Function Points to Size and Effort
The Adjusted Function Points cell below was derived from the previous worksheet. Enter this number next to the programming language being used. The worksheet will calculate source code size and person months.
If more than one language is being used, disregard the Calculated Function Points cell. Use the FP from each worksheet and enter all FP into the table below.
| Adjusted Function Points | 0
| Programming Language | Language Group | Language Level | Avg Source Statements per FP | Calculated FP | Source Code Size | Function Points per Person Month | Person Months
| Access | 3 | 8.5 | 38 |  |  | 15.42
| ADS/On-line | 4 | 16 | 20 |  |  | 15
| ANSI Basic | 2 | 5 | 64 |  |  | 12.5
| AppleSoft Basic | 1 | 2.5 | 128 |  |  | 8.75
| Assembler | 1 | 1.5 | 213 |  |  | 6.25
| Basic A | 1 | 2.5 | 128 |  |  | 8.75
| C (default) | 1 | 2.5 | 128 |  |  | 8.75
| C++ (Visual C++) | 3 | 9.5 | 34 |  |  | 16.58
| C++ (default) | 2 | 6 | 53 |  |  | 15
| CGI | not available
| CICS | 2 | 7 | 46 |  |  | 17.5
| COBOL (MicroFocus) | 2 | 4 | 80 |  |  | 10
| COBOL (default) | 1 | 3 | 107 |  |  | 10
| CULPRIT | 5 | 25 | 13 |  |  | 30.65
| dBase IV | 3 | 9 | 36 |  |  | 16
| EASEL | 3 | 11 | 29 |  |  | 18.33
| EDA/SQL | 5 | 27 | 12 |  |  | 31.94
| EXCEL 5 | 6 | 57 | 6 |  |  | 40.71
| FOCUS | 2 | 8 | 40 |  |  | 20
| FORTRAN | 1 | 3 | 107 |  |  | 10
| HTML 3.0 | 4 | 22 | 15 |  |  | 27.86
| IBM CICS/VS | 2 | 8 | 40 |  |  | 20
| IBM VS COBOL II | 1 | 3.5 | 91 |  |  | 11.25
| IDMS | 2 | 8 | 40 |  |  | 20
| IEF | 4 | 23 | 14 |  |  | 30
| IMPROMPTU (Dec Spt Default) | 3 | 9 | 36 |  |  | 16
| INFORMIX's 4GL | 2 | 8 | 40 |  |  | 20
| JAVA | 2 | 6 | 53 |  |  | 17.5
| JCL | 1 | 1.45 | 221 |  |  | 6.13
| MARK IV | 2 | 8 | 40 |  |  | 20
| Microsoft SQL/Server [DB default] | 2 | 8 | 40 |  |  | 20
| MOTIF (X-Windows) [3rd gen def] | 2 | 4 | 80 |  |  | 10
| OO (default) | 3 | 11 | 29 |  |  | 18.33
| ORACLE's 4GL | 2 | 8 | 40 |  |  | 20
| PC FOCUS | 3 | 9 | 36 |  |  | 16
| PeopleTools | 3 | 9 | 35 |  |  | 16
| PERL | 3 | 12 | 27 |  |  | 19.5
| PL/1 | 2 | 4 | 80 |  |  | 10
| QMF | 4 | 22 | 15 |  |  | 27.86
| REXX (MVS) | 2 | 4 | 80 |  |  | 10
| SAS | 3 | 10 | 32 |  |  | 17.17
| SIMPLAN | 3 | 9 | 36 |  |  | 16
| SQL | 5 | 25 | 30 |  |  | 30.65
| SQL/Windows (Centura) | 5 | 27 | 12 |  |  | 31.94
| Sybase | 2 | 8 | 40 |  |  | 20
| Tuxedo | not available
| UNIX (shell scripts) | 1 | 3 | 107 |  |  | 10
| Visual BASIC 3 | 3 | 10 | 32 |  |  | 17.17

## WAVE
Weighted AVErage (WAVE) Guidelines
The WAVE approach is used to calculate an average value from the best case (most optimistic), worst case (most pessimistic), and the most likely estimates.
These estimates can be developed by one person, or a group, who have some knowledge of the activity. The WAVE approach helps in defining assumptions related to the best, worst, and most likely cases associated with an activity.
Estimates can be high-level (Stage only) or refined to individual tasks. The MS Project Plan Template can be copied into the table below to list the Stages and Tasks.
Note that QS activities are typically 10% of total project hours. SCM activities are typically 5% of total project hours.
Do not make entries in shaded rows or columns. After copying the MS Project Plan Template, drag the red shaded columns down to expand the formulas to match the stages and tasks copied in.
When finished, skip a row and enter the sum sign in the WAVE column to obtain Total Project Hours.
Most Likely
Stage | Task | Best Case | Worse Case | Most Likely | Weighted | WAVE
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0
[5 empty] | 0 | 0

## Use Cases to Effort
Use Case Estimation Guidelines
The weights apply to the composite of entries for an element, i.e. the weight is for all actors, not individual actors. Use the tables below to complete the table. Make entries in the unshaded areas only.
Element | Weight | Step | Calculation
AWF |  | 1 Weight the Actors | None
UCWF |  | 2 Weight the Use Cases | None
UUCP |  | 3 Calculate the Unadjusted Use Case Points | 0
TCF | 0 | 4 Weight the Technical Complexity Factors | None
EF | 0 | 5 Weight the Environmental Factors | None
UCP |  | 6 Calculate the Use Case Points | 0
HOURS |  | 7 Determine Staff-hours per UCP | None
EFFORT |  | 8 Calculate the Total Effort | 0 | In hours
|  |  | 0 | In weeks
STEP 1 | Weight the Actors (AWF)
| Actor Type | Description | Factor
| Simple | Program Interface | 1
| Average | Interactive, or protocol-driven interface | 2
| Complex | Graphical interface | 3
STEP 2 | Weight the Use Cases (UCWF)
Use Transaction-Based Weighting
| Use Case Type | Description | Factor
| Simple | 3 or fewer transactions | 5
| Average | 4 – 7 transactions | 10
| Complex | More than 7 transactions | 15
OR Class-based Weighting:
| Use Case Type | Description | Factor
| Simple | Fewer than 5 analysis classes | 5
| Average | 5 – 10 analysis classes | 10
| Complex | More than 10 analysis classes | 15
Step 3 | Calculate the Unadjusted Use Case Points (UUCP)
UUCP = AWF + UCWF
Step 4 | Weigh the Technical Complexity Factors (TCF)
Total all the factors that apply
| Factor Number | Factor Description | Weight | Project
| T1 | Distributed system | 2
| T2 | Response or through performance objectives | 1
| T3 | End-user efficiency (online) | 1
| T4 | Complex internal processing | 1
| T5 | Code must be reusable | 1
| T6 | Easy to install | 0.5
| T7 | Easy to use | 0.5
| T8 | Portable | 2
| T9 | Easy to change | 1
| T10 | Concurrent | 1
| T11 | Includes special security features | 1
| T12 | Provides direct access for third parties | 1
| T13 | Special Training facilities are required | 1
|  |  | Total | 0
Step 5 | Weight the Environmental Factors (EF)
Total all the factors that apply
| Factor Number | Factor Description | Weight | Project
| F1 | Familiar with UML/ICONIX process | 1.5
| F2 | Application experience | 0.5
| F3 | Object-oriented experience | 1
| F4 | Lead analyst capability | 0.5
| F5 | Motivation | 1
| F6 | Stable requirements | 2
| F7 | Part-time developers | -1
| F8 | Difficult programming language | -1
|  |  | Total | 0
Step 6 | Calculate the Use Case Points (UCP)
UCP = UUCP * TFC * EF
Step 7 | Determine Staff-hours per UCP
Review Environmental Factors (EF): Count how many of F1 through F6 are below 3 and how many in F7 through F8 are above 3. If the total is 2 or less, enter 20 staff-hours per UCP. If the total is 3 or 4, enter 28 staff-hours per UCP. If the total is 5 or more, attempt to make changes to your project so the numbers can be adjusted.
Step 8 | Calculate the Total Effort
(UCP * Staff-hours rounded up to the nearest hour) + 3 weeks

## Documentation
Technical Publications Development Time Estimates
Industry standards for estimating documentation schedules apply.
Estimates will vary depending upon the writer’s experience with the product and the complexity of the information.
 New pages = 4 – 6 hours per page
 Change pages = 2 – 4 hours per page
 Online Help = 5 – 8 hours per topic
1. Additional factors in estimating:
a. For a User’s Guide, factor 1 page for every three menu items. This will include new functions at the user interface level. Refer to existing documentation of similar functionality to develop a rough page count estimate.
b. For installation, assume that a new port or product update requires a change to every page of the installation chapter (or manual) for that product. If this is a new product, count the pages of a similar existing installation manual to get a new page count.
Note: In the time estimate tables below, one working day is equal to 7 hours of actual writing time. One hour per day is allocated to administrative tasks such a meeting attendance.
{PROJECT NAME} (project being estimated)
Make entries in Pages per Topics and Hours per Topic only
Topics | Pages per Topic | Hours per Page | Hours | Days
User's Guide |  |  | 0 | 0
Installation Guide |  |  | 0 | 0
2. Beta Help Development Estimates
The following table shows the estimated time required to develop/write the 1st draft of the Beta Help.
Example:
50 topics at 5 hours per topic = 250 hours
divide by 7 hours per day = 35.7 days
round up to 36 days |  |  |  |  | {PROJECT NAME} (project being estimated)
Make entries in New Topics and Hours per Topic only
New Topics | Hours per Topic | Hours | Days |  | New Topics | Hours per Topic | Hours | Days
50 | 5 | 250 | 36 days |  |  |  | 0 | 0
3. Commercial Help Development Estimates
The following table shows the estimated time required to develop/write the 1st draft of the Commercial Help.
Example:
5 new complex topics at 8 hours per topic
total = 40 hours
divide by 7 hours per day = 5.7 days
round up to 6 days
10 revised topics (minor revisions) at 2 hours per topic
total = 20 hours
divide by 7 hours per day = 2.8 days
round up to 3 days
{PROJECT NAME} (project being estimated)
Make entries in Topics and Hours per Topic only
| Topics | Hours per Topic | Hours | Days |  |  | Topics | Hours per Topic | Hours | Days
New | 5 | 8 | 40 | 6 |  | New |  |  | 0 | 0
Revised | 10 | 2 | 20 | 3 |  | Revised |  |  | 0 | 0
4. Commercial Release Notes Development Estimates
The following table shows the estimated time required to develop/write the 1st draft of the Release Notes. For this project, Release Notes will be provided only at Commercial release.
Example:
10 pages at 4 hours per page
total = 40 hours
divide by 7 hours per day = 5.7 days
round up to 6 days |  |  |  |  | {PROJECT NAME} (project being estimated)
Make entries in New Pages and Hours per Page only
New Pages | Hours per Page | Hours | Days |  | New Pages | Hours per Page | Hours | Days
10 | 4 | 40 | 6 |  |  |  | 0 | 0
Summary of Tech Pubs Development Estimates
The estimates below include both Tech Pubs development/writing time and review time.
Example: | Expressed in Days
Document or Help | Develop 1st draft | Review time | Develop 2nd draft | Review time | Revise/ fix bugs | Total
1a. Users Guide | 0 |  |  |  |  | 0
1b. Installation Guide | 0 |  |  |  |  | 0
2. Beta Help | 36 | 5 | 5 | 5 | 4 | 55
3. Commercial Help | 9 | 5 | 3 | 5 | 3 | 25
4. Release Notes | 6 | 5 | 2 | 5 | 2 | 20
{PROJECT NAME} (project being estimated)
Make no entries in Develop 1st draft column or Total column
Document or Help | Develop 1st draft | Review time | Develop 2nd draft | Review time | Revise/ fix bugs | Total
1a. Programmers Guide Functions
1b. New Functions, User
1c. Users Guide
1d. Installation Guide
2. Beta Help | 0 | 5 | 5 | 5 | 4 | 19
3. Commercial Help | 0 | 5 | 3 | 5 | 3 | 16
4. Release Notes | 0 | 5 | 2 | 5 | 2 | 14

## Computer Resources
Definition of Critical Computer Resources for [ Insert Project Name here ]
| Name | Office Number / Mobile Number
Product Manager Name:
Project Manager Name:
I.T. Manager Assigned:
|  |  | Yes | No | Version/ Service Pack
1. Does the system require a network connection?
If the answer is "Yes," insert rows below and indicate how many and what speeds.
2. Does the system require connection to NT resources?
If the answer is "Yes," insert rows below and indicate which resource(s).
3. Does the system require connection to Novell resources?
If the answer is "Yes," insert rows below and indicate which resource(s).
4. Does the system require a web server?
5. Does the system require an application server?
a. If “Yes,” is there an explicit requirement that the web and application services reside
on separate machines?
6. Does the system require a database server?
a. If “Yes,” what DBMS is required? Place check in Yes column.
Microsoft SQL Server 7.0
Microsoft SQL Server 2000
Oracle 8I
FoxPro
Visual FoxPro
Other (include revision) Enter in next column
ANSWER THE FOLLOWING IN THE YES COLUMN
b. What is the anticipated drive size?
(As an alternative, approximately how many tables are in the database model?)
c. What are the estimated maximum transactions per second?
d. How long must data be kept available on disk?
e. How often should the database be backed up?
f. How often should the transaction log be backed up?
g. What are the expectation for data archiving?
h. What are the expectations for growth of data?
7. How much disk space does the application—not data or metadata—require? (in MB)
8. What are the expected peak periods of system usage?
9. How many users will use the system during peak periods?
10. How much RAM does the system require during peak periods?
11. What are the expected normal periods of usage?
12. How many users will use the system during normal periods?
13. How much RAM does the system require during normal periods?
14. What software—including the OS or Network Software—needs to be installed on the application or web server? List using letters, i.e. a., b., etc.
15. What are the availability expectations? (e.g., Business Hours, 24x5, 24x7)
16. Does the system have provisions for manual work-around if it is unavailable?
If the answer is "Yes," insert rows below and indicate the work-around.
17. What are the reliability expectations?—in other words, define what is an “unacceptable” length of “down” time for recovery? (e.g., 4 hours, 8 hours, 24 hours, 1 week)
18. What provisions need to be made for firewalls or other security measures?